JISC/HEA Project Plan

Before completing this template please note:

- This template is for completion by JISC/HEA funded projects

- Text in blue italics is explanatory and should be deleted in completed documents.

- The Project Management Guidelines (www.jisc.ac.uk/proj_manguide.html) explain the purpose of Project Plans.

- Please remember to fill in the information on the header - i.e. doc version, contact and date)

| Project Information |
| --- |
| Project Identifier | To be completed by HEA |
| Project Title | Embedding OER Practice |
| Project Hashtag | #embeddingoerpractice |
| Start Date | November 2011 | End Date | October 2012 |
| Lead Institution | University of Lincoln |
| Project Director | N/A |
| Project Manager | Sue Watling |
| Contact email | swatling@lincoln.ac.uk |
| Partner Institutions | N/A |
| Project Webpage URL | http://oer.lincoln.ac.uk |
| Programme Name | HEFCE/JISC/Higher Education Academy Open Educational Resources Programme: Higher Education Institutional Change (HEIC) Strand. |
| Programme Manager |  |

| Document Information |
| --- |
| Author(s) | Sue Watling |
| Project Role(s) | Project Coordinator |
| Date | January 2012 | Filename |  |
| URL |  |
| Access | This report is for general dissemination |

| Document History |
| --- |
| Version | Date | Comments |

Table of Contents

NB : This table of contents ‘auto-populates’ - to update the table of contents – place cursor in the table of contents, right-click your mouse, click ’update field’, select appropriate option

1.	Project Overview	3

1.1	Project Summary	3

1.2	Objectives	3

1.3	Anticipated Outputs	4

1.4	Overall Approach	5

1.5	Anticipated Impact	5

1.6	Stakeholder Analysis	6

1.7	Related Projects	7

1.8	Constraints	7

1.9	Assumptions	7

1.10	Risk Analysis	7

1.11	Technical Development	8

1.12	Standards	8

1.13	Intellectual Property Rights	9

2	Project Resources	9

2.1	Project Partners	9

2.2	Project Management	9

2.3	Project Roles	10

2.4	Programme Support	11

3	Detailed Project Planning	11

3.1	Evaluation Plan	11

3.2	Quality Assurance	13

3	Dissemination Plan	14

3.4	Exit and Embedding Plans	15

3.5	Sustainability Plans	15

Appendices	16

Appendix A. Project Budget	16

Appendix B. Workpackages	16

1. Project Overview

## 1.1	Project Summary

‘Embedding OER Practice’ at the University of Lincoln will promote the philosophy and practice of Open Educational Resources (OER) for teaching and learning. Six project teams consisting of academic staff, professional support staff and students have been established. Teams will investigate the reuse and repurposing of OER across a range of generic learning experiences and establish appropriate dissemination pathways for ensuring sustainable practice. Projects will run in parallel with a HEA Change Academy initiative looking to identify opportunities to embedding OER practice at both local and institutional levels.

## Objectives

- raise institutional awareness of the philosophy and practice of OER

- collaborate with cross-institutional teams to promote and embed OER.

- establish support and guidance for engaging with OER.

- work alongside the HEA Change Academy to plan and develop strategies for embedding OER

Objective 1: increased institutional awareness of the philosophy and practice of OER

S –OER practice to be promoted across the university via poster, leaflet and handbook materials and through the dissemination of outputs from individual project teams

M – OER practice will be embedded into the curriculum and staff and student awareness of OER surveyed at the project end

A – project work will build on and expand existing knowledge and interest in open education within the institution

R – expert technical and pedagogical support in place with regard to OER practice

T – by September 2012 increased use of OER will have been promoted and established

Objective 2: collaborate with cross-institutional teams to promote and embed OER

S – OER used to support generic aspects of the student experience.

M – Project team outputs will include a minimum of one example of repurposed or new OER made publically accessible through an OER repository.

A – Projects reflect generic learning experiences relevant to teaching and learning in higher education.

R – Development funding available to support achievement of objectives.

T – By September 2012 projects will have outputs in place for Semester A 2012/13.

Objective 3: establish support and guidance for engaging with OER

S – The project website http://oer.blogs.lincoln.ac.uk to transition into online community supporting OER practice with signposting to further information.

M – Online OER community visits recorded and staff surveyed to establish effectiveness of promotion campaign and evidence changes in practice.

A – Expertise within the project team and external alignment with specialist support for educational technology and graphic design established.

R – http://oer.blogs.lincoln.ac.uk will develop during the project and projects outputs provide content for embedding OER practice.

T – by September 2012 the website at http://oer.blogs.lincoln.ac.uk will be the OER online community. Promotion materials and staff handbook will be completed.

Objective 4: work alongside the HEA Change Academy to plan and develop strategies for embedding OER

S – Sustainable approaches to develop strategies for embedding OER integral to Change Academy programme.

M – Project evaluations and Change Academy dissemination process.

A – Change Academy programme to support the development of whole institution strategies to effect lasting change.

R – Individual projects offer realistic opportunities for cultural change at local level.

T – by September 2012, the Change Academy programme will be completed and individual project outputs delivered.

## Anticipated Outputs

| Output / Outcome Type (e.g. report, publication, software, knowledge built) | Brief Description |
| --- | --- |
| Output: online community supporting OER, Outcome: a one-stop-shop for accessing support for embedding OER and signposting additional information, | The project website at http://oer.blogs.lincoln.ac.uk will provide an information base during the life span of the project. Core information will provide foundation for the online community supporting OER Practice with additional content deriving from project workshops and dissemination of individual project outputs and deliverables. |
| Output: ‘Embedding OER Practice’ promotion campaign, Outcome: increased awareness of the philosophy and practice of OER, | Posters, leaflets and an OER handbook will support raising awareness of OER across the institution and provide signposting for additional information and examples of best practice. |
| Output: Collection of OER relating to generic aspects of teaching and learning in a digital age. Outcome: increased opportunities to debate the value of open education, to share educational materials and promote these experiences at departmental level and beyond. Increased staff confidence and competence working with digital educational environments. | OER will be scoped, developed and embedded into existing practices to support transition into higher education with regard to library and information skills, for encouraging early reflective writing, for embedding employability in the undergraduate curriculum and investigating how OER can support the construction of e-Portfolios in practice. A short online course on teaching and learning with educational technologies will be developed using OER and added to the Teacher Education portfolio. These cross institutional examples of the use of OER, and the value of reusing and repurposing to adapt to subject specialism, will offer multiple opportunities for the promotion and evidencing of OER practice. |
| Output: evidence of embedding and disseminating OER. Outcome: sustainable changes in practice which support philosophy and practice of open education and increase confidence and competence working within virtual teaching and learning environments | Working with the HEA Change Academy, project teams will identify opportunities for embedding change practices using OER at departmental level. These are expected to reflect a variety of different approaches as project teams address different areas of the student experience but for all teams the process of embedding OER will offer real-time opportunities for engagement with virtual learning and teaching opportunities and developing those digital literacies most appropriate for teaching, learning and professional practice in a digital age. |

## Overall Approach

Six project teams will focus on embedding the philosophy and practice of OER in their own disciplines. Each team has developed an individual work package (see Appendix 2) which identifies objectives, tasks, outputs and responsibilities.  Selecting generic aspects of the teaching and learning will maximise opportunities for dissemination across Departments, Schools and Faculties. The team projects are focusing on the following six areas:

- Supporting transition with OER with regard to developing library and information skills

- Using OER for Early Reflective Writing

- OER for embedding employability in the undergraduate curriculum

- How OER can support the construction of e-Portfolios in practice

- Exploring and embedding the use of OER on PGCert/HE…and Beyond

- Behind the Scenes technical support for OER

Teams comprise academic staff, professional support staff and students. Addressing the scoping, reusing and repurposing of OER for teaching and learning will enhance individual confidence and competence with virtual learning technologies while supporting the development of those digital literacies most appropriate for teaching, learning and professional practice in a digital age.  Project dissemination will be supported through engagement with the HEA Change Academy programme and with support from Change Academy critical friends.

Critical success factors

Development of effective repository search strategies and recognition of creative common licences

Expertise with appropriate copyright and Digital Rights Management (DRM) knowledge with regard to all digital content found on the Internet

Establishing individual staff and student confidence and competence working within digital technologies for teaching and learning

Increased awareness of appropriate virtual pedagogies and the construction of effective online learning experiences

## Anticipated Impact

| Impact Area | Anticipated Impact Description |
| --- | --- |
| Maintain research excellence. | Contribute to growing the institutional research capacity Support institutional ambition for research active staff Increase recognition and enhance reputation for institutional expertise in open education and technology for learning Provide opportunities for new partnerships and linkages across Faculties and subject areas |
| Maintain teaching and learning excellence. | Staff impact Support collaborative approaches to teaching and learning and the sharing of knowledge and expertise Create opportunities for innovation and experimentation Increase the availability of quality peer reviewed material to enhance the curriculum Encourage attention to quality of online learning materials and effectiveness of online learning experiences Greater efficiency in materials production Access to peer to peer feedback and review Improve design and delivery Accreditation for CPD processes Reputational benefits via recognition for resource development Student impact Involvement in central research and development process Opportunity to give feed back and review content Increased availability and flexibility of resources Broader access to content via affordances of anytime anywhere virtual learning Subject specific learning development opportunities through release of generic OERs that can be re-used and recontextualised in different subject areas |
| Be more effective/save money. | Re-use and re-purposing of existing content saving preparation time. Increased availability of teaching and learning materials Development of customisable generic templates supports sharing across disciplines. Repository culture offers a one-stop-shop for establishing new teaching practice or enhancing existing practice. |
| Have a positive impact on wider society. | Employers benefit from access to re-purposable content Creation of new potential partnerships with content providers Removal of barriers to learning and increased widening participation in educational opportunities |
| Be ready for technology needs in the future. | Attention to appropriate digital literacies essential for teaching, learning and professional practice opportunity for networking and sharing expertise across the sector |

## Stakeholder Analysis

| Stakeholder | Interest / stake | Importance (H/M/L) |
| --- | --- | --- |
| JISC | Project funder | High |
| Higher Education Academy (HEA) | Project funder | High |
| HEFCE | Project funder | High |
| VC, PVC and Senior Management | Benefits of institutional engagement with sector wide OERUK and OER Change Academy programmes. | High |
| Academic Staff and Professional Support Staff | Opportunities for engagement with the philosophy and practice of OER. Experience of the benefits of sharing expertise. Participation in the OER Change Academy programme. | High |
| Education Technology Staff | Increased support for issues of creative common licensing, IPR and copyright of digital content. Maintenance and support of repository environment. | High |
| Students | Opportunity to enhance student experience through contribution to research activities, digital scholarship and engagement in active production of knowledge | High |

## Related Projects

N/A

## Constraints

N/A

## Assumptions

N/A

## Risk Analysis

| Risk Description | Probability (P) 1 – 5 (1 = low 5 = high) | Severity (S) 1 – 5 (1 = low 5 = high) | Risk Score (PxS) | Detail of action to be taken (mitigation / reduction / transfer / acceptance) |
| --- | --- | --- | --- | --- |
| Key staff leaving before project completion | 2 | 2 | 4 | Additional pool of interested critical friends and supporters identified from the start of the project. |
| Key staff absence or unavailability | 3 | 2 | 6 | Additional time built into work schedules, capacity for flexibility and sharing roles key to distribution of tasks, expected absence highlighted from the start of the project. |
| Logistical difficulties with maintaining contact with teams dispersed across the campus who have flexible working practices. | 3 | 2 | 6 | Central online communication systems established for sharing content. Skype used for virtual meetings. |
| Maintaining contact between teams and critical friends from Change Academy. | 2 | 1 | 3 | Schedule of Change Academy meetings. Email and Skype used to maintain contact between meetings. |
| Courses or modules chosen to pilot OER practice being identified for closure or transfer to other institutions | 2 | 3 | 6 | Generic nature of chosen areas and portability of OER increases likelihood of appropriate transfer to other awards or units. |
| IPR issues related to individual OERS | 4 | 2 | 8 | Workshops for awareness raising and support, guidance on project website, IPR expertise within project teams (JW and PS Team Six) |
| Failure to provide inclusive design and ensure maximum accessibility of OER | 4 | 3 | 12 | Complete set of TechDis Accessibility Essentials series distributed to all teams. Expertise within the team on inclusive practice with digital content (SW project coordinator) |
| Lack of technical support for teams. | 2 | 4 | 8 | Project team developed to offer expert technical support and advice. Regular workshops and online/telephone support mechanisms put in place. |
| Problems with embedding change at Departmental, Faculty or College level | 4 | 3 | 12 | Achieving early buy in from VC, PVC, Deans, Senior Managers and Heads of Departments. |

## Technical Development

N/A

## Standards

| Name of standard or specification | Version | Notes |
| --- | --- | --- |
| RSS |  | Used for syndicating course content |
| Atom |  | Used for syndicating course content |
| Simple Dublin Core |  | Used for describing course content within the IR and in HTML |
| OPML |  | Used for exchanging web feeds and creating ‘reading lists’ |
| PDF |  | Used for printable documentation |
| ODF |  | Used for printable documentation (ODT) and slide presentations (ODP) |

## Intellectual Property Rights

All project documentation, policy documents and training materials will be made available under a CC-BY license. Code will be licensed under an open source license and we will seek advice from OSSWatch on this matter. Data managed by the pilot infrastructure will be subject to copyright and licensing specific to the dataset, although we will seek to ensure some publicly accessible data is available to demonstrate the functionality of the web interface and APIs.

MIT use CC-BY-NC-SA

# Project Resources

## 2.1	Project Partners

N/A

## Project Management

The project will be led and managed within the Centre for Educational Research and Development (CERD) at the University of Lincoln.  Sue Watling, Learning and Teaching Coordinator within CERD, will be responsible for decisions relating to the management of day-to-day project activity and budgets.  These will include:

- Preparing the project plan

- Coordinating and managing project work

- Monitoring project progress and performance

- Ensuring that project outputs are delivered on time

- Identifying risks, problems, and issues, and escalating them as appropriate

- Managing communication within the project

- Preparing progress, final, and other reports

- Arranging meetings and keeping records

- Managing project resources, including the budget

- Coordinating work on any legal agreements, e.g. consortium, vendor, or license agreements

- Maintaining the project web site

- Maintaining project documentation

- Ensure that the project abides by the letter of grant, the JISC Terms and Conditions, and the JISC Project Management guidelines

Individual teams will manage their own independent projects designed to promote and embed OER Practice within their own subject areas while establishing opportunities for dissemination across their departments, schools and faculties.

## Project Roles

| Team Member Name | Role | Contact Details | Days per week to be spent on the project |
| --- | --- | --- | --- |
| Sue Watling Teaching and Learning Coordinator CERD | Project Coordinator | swatling@lincoln.ac.uk | 0.3 FTE |
| Andy Hagyard Teaching and Learning Coordinator CERD | Team Leader: Supporting transition with OER with regard to developing library and information skills | ahagyard@lincoln.ac.uk | 0.025 FTE |
| Julie Burton Senior Lecturer Health and Social Care | Team Leader: Using OER for Early Reflective Writing | jburton@lincoln.ac.uk | 0.025 FTE |
| Jill Jameson Senior Lecturer School of Social Sciences | Team Leader: OER for embedding employability in the undergraduate curriculum | jjameson@lincoln.ac.uk | 0.025 FTE |
| Karin Crawford Principal Teaching Fellow School of Health and Social Care | Team Leader: How OER can support the construction of e-Portfolios in practice | kcrawford@lincoln.ac.uk | 0.025 FTE |
| Aileen Morris Principal Teaching Fellow CERD | Team Leader: Exploring and embedding the use of OER on PGCert/HE…and Beyond | aimorris@lincoln.ac.uk | 0.025 FTE |
| Julian Beckton Teaching and Learning Coordinator CERD | Team Leader: ‘Behind the Scenes’ technical support for OER | jbeckton@lincoln.ac.uk | 0.025 FTE |

Training needs

Technical support: embedding OER Practice Workshops will address the scoping and searching of repositories, identifying open content, understanding copyright and IP issues, selecting appropriate creative commons licences and be followed up with written and online resources.  Additional technical support will be available via a FAQ list and email.

Inclusive practice with digital data: individual packs of TechDis Accessibility Essentials Resources have been distributed to teams with the equivalent content being made available online via the http://oer.blogs.lincoln.ac.uk website.

## Programme Support

Support for the programme is available from the HEA OER project management team and the HEA Change Academy critical friends.

# Detailed Project Planning

## 3.1	Evaluation Plan

| Timing | Factor to Evaluate | Questions to Address | Method(s) | Measure of Success |
| --- | --- | --- | --- | --- |
| Jan - Mar | Awareness of history of open education, the philosophy and practice of OER and existing use of OER | Are staff familiar with the open education movement, understand how to identify OER, have effective repository search strategies and recognise different creative commons licences? Are staff already using OER? | Initial meetings between Project Coordinator and Team leaders and teams. Establishing OER support workshops. Project website | Response from staff and students Ongoing project review and reflection |
| Feb-Apr | Scoping and evaluation of existing OER content with decisions regarding use and reuse | Establishing subject criteria against which to measure OER, appropriate keywords for searching and guidelines for selection e.g. quality, learning level and accessibility | Individual team meetings and analysis of outputs. Guidelines for dissemination across department. | Response from staff. |
| Feb–Jul | Creating learning areas using OER | Reuse and repurposing OER | Critical review of content within teams and by students | Teaching and learning materials leading to effective learning experiences which have been piloted and reviewed |
| Feb-Sept | OER promotion campaign | Raising awareness of OER and providing signposting for further information | Design and distribution of posters, leaflets and staff handbook for embedding OER Practice, utilising existing information channels such as institutional newsletters | Positive feedback from staff and students Increased users stats for project website Survey of staff attitudes towards OER |
| Aug – Oct | Ongoing cultural change | What impact has the Embedding OER Practice project had within teaching and learning across the institution? | How much new teaching and learning content has been developed and licenced as OER? Analysis and sharing of individual project dissemination routes. | Positive feedback from departmental and faculty teaching and learning committees. Responses to project websites Project Report |

## 3.2	Quality Assurance

| Output / Outcome Name | Online community supporting OER |
| --- | --- |
| When will QA be carried out? | Who will carry out the QA work? | What QA methods / measures will be used? |
| Throughout the project | Project management team | Accessibility, Usability and Adherence to standards e.g. JISC web format and image standards. |
| Output / Outcome Name | Embedding OER promotion campaign |
| When will QA be carried out? | Who will carry out the QA work? | What QA methods / measures will be used? |
| Throughout the project | Project management team | Fitness for purpose, Accessibility and principles of inclusive design, piloting and evaluating with critical friends, OER project teams and focus groups of staff and students |
| Output / Outcome Name | Collection of OER relating to generic aspects of teaching and learning in a digital age. |
| When will QA be carried out? | Who will carry out the QA work? | What QA methods / measures will be used? |
| Throughout the project | Project management team | Piloting and evaluating with critical friends, OEr project teams and focus groups of staff and students |
| Output / Outcome Name | Evidence of embedding and disseminating OER |
| When will QA be carried out? | Who will carry out the QA work? | What QA methods / measures will be used? |
| Throughout the project | Project management team Project Champions | Teaching and Learning Committee minutes Project reviews and reflections |

## 3.3	Dissemination Plan

| Timing | Dissemination Activity | Audience | Purpose | Key Message |
| --- | --- | --- | --- | --- |
| Throughout the project | OER promotion campaign | Academic staff Professional support staff Students | Encourage staff and students to engage with OER practice. Supporting change culture. | Raising awareness of the use and reuse of OER for teaching and learning |
| Throughout the project | Project website will record progress, outcomes and dissemination while providing a platform for discussion and debate around the use of OER in higher education. Project website with transition online community supporting OER Practice | Internal and external staff in educational sector HEA/JISC | Widen awareness of open education movement and OER Support, guidance and signposting for additional information | Promotion of the project and of OER Value of sharing expertise and teaching and learning resources |
| Throughout the project | Promotion and sharing of learning opportunities based on OER content | Academic and professional support staff engaged in teaching and learning activities | Integration into the curriculum, teaching practice, Teacher Education portfolio and opportunities for evidencing CPD | Technology for education and the open educational movement are integral to teaching and learning in 21st century |
| Throughout the project | Project promotion at internal teaching and learning committees, programme events, awaydays, newsletters and other appropriate occasions | Heads of Departments, Senior Management, | Raise awareness of staff engagement in funded OER projects and potential research activities | Impetus for change can be organic and originate from staff engaged with teaching and learning. Supporting a culture of change. |
| Throughout the project | Presentations at internal and external events and conferences for teaching, learning and technology for education e.g. JISC, ALT, SEDA, HEA, | Staff and students plus the wider education sector | Promoting OER, raising awareness of best OER practice within teaching and learning | Promoting the advantages of open education, creative commons and the sharing of expertise, across the sector |
| Throughout the project | Publications in journals and newsletters; for example ALT, HEA Subject Centres, SEDA and internal all staff, all student and Faculty newsletters. | Staff and students plus the wider education sector | Promoting OER, raising awareness of best OER practice within teaching and learning | Promoting the advantages of open education, creative commons and the sharing of expertise, across the sector |

## 3.4	Exit and Embedding Plans

| Project Outputs/Outcomes | Action for Take-up & Embedding | Action for Exit |
| --- | --- | --- |
| Online community supporting OER | Community hosted and technically maintained via institutional network. | Community will remain ‘live’ after the project has ended. |
| Embedding OER promotion campaign | Distribution of OER handbook to all academic and professional support staff. Project reports available on OER community site. | No further exit plan required. |
| Collection of OER relating to generic aspects of teaching and learning in a digital age. | Resources made publically available for reuse and repurposing via repository. | Embedding OER practice in curriculum and teacher education programme. |

## 3.5	Sustainability Plans

| Project Outputs/Outcomes | Why Sustainable | Scenarios for Taking Forward | Issues to Address |
| --- | --- | --- | --- |
| Online community supporting OER | Hosted and maintained by institution after the project | Discussions with team leaders and project champions. | Future responsibility for updating and adding new content. |
| Embedding OER promotion campaign | Promotion materials continue to be available across the institution. | OER practice continues to be promoted and staff supported to make additional content available as OER. | Maintaining public profile of OER practice. |
| Collection of OER relating to generic aspects of teaching and learning in a digital age. | OER publically available for reuse and repurposing. | Individuals continue to use OER and promote OER practice to colleagues. | Strategic approaches to adopting OER practice across the institution. |

# Appendices

## Appendix A. Project Budget

## Appendix B. Workpackages