# JISC/HEA WORK PACKAGE

| WORKPACKAGES | Month | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Project Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: To review previous transition projects at Lincoln and from across the sector |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3: To review existing OERs to support transition, both within the institution and externally |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4: To explore appropriate tools for the development of OERs |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5: To develop and adapt OERs to support Getting Started 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6: To evaluate the effectiveness of resources used… |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7: To develop strategy for embedding OER practice in support for transition |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10: |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Project start date: Jan 2012

# Project completion date: 31 Oct 2012

Duration: 10 months

| Work package and activity | Earliest start date | Latest completion date | Outputs (clearly indicate deliverables & reports in bold | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| WORKPACKAGE 1: Project management Objective: To establish mechanisms for communication, evaluation and dissemination of the project |  |  |  |  | All |
| Develop Project Website | 16/01/12 | 31/01/12 | Wordsite operational |  | AH + all |
| Establish evaluation criteria |  | 31/01/12 | Evaluation framework on website |  | All |
| Identify dissemination outputs |  | 31/10/12 | Journal article(s) / Conference papers Contribute to final project report |  | All |
| Agree schedule of meetings |  | 31/01/12 | Calendar on website |  | All |
| WORKPACKAGE 2: Objective: To review previous transition projects at Lincoln and from across the sector in order to assess the needs of students prior to arrival and through induction | 01/02/12 | 01/03/12 |  |  |  |
| Review of 2011 Getting Started evaluation | 01/02/12 | 24/02/12 | Review report |  | MN / AB |
| Literature Review of initiatives across HE sector |  | 24/02/12 | Literature review on website |  | AH |
| Survey of local 6th form students and staff |  | 24/02/12 | Survey data and summary report |  | OM |
| Focus Group with Student Reps |  | 24/02/12 | Summary report |  | OM |
| Identification of priority areas for development in relation to library and learning development |  | 01/03/12 | List of topic areas to inform subsequent workpackages | 1 | All |
| WORKPACKAGE 3: Objective: To review existing OERs to support transition, both within the institution and externally | 01/03/12 | 31/03/12 |  |  | ALL |
| Allocation of topic areas as identified in WP 1 |  | 02/03/12 | Each team member to have designated area |  | All |
| Review of internal resources | 02/03/12 | 23/03/12 | UL resources identifed |  | All |
| Identification of external repositories and other sources | 02/03/12 | 23/03/12 | List of external resources for each area |  | All |
| Produce report | 16/03/12 | 31/03/12 | Guide to use of repositories | 2 | AH |
| WORKPACKAGE 4: Objective: To explore appropriate tools for the development of OERs | 01/02/12 | 30/04/12 |  |  | All |
| Identification of relevant software | 01/02/12 | 16/03/12 | Annotated list placed on website |  | All |
| Evaluation of 2/3 tools (xerte, screenr, articulate??) | 16/03/12 | 13/04/12 | Brief evaluation on website |  | All |
| Produce report | 01/04/12 | 30/04/12 | Guide to use of open source software for resource development | 3 | AH |
| WORKPACKAGE 5: Objective: To develop and adapt OERs to support Getting Started 2012 | 01/04/12 | 31/07/12 |  |  | All |
| Dependent on outcomes of workpackages 1-3 – develop and pilot OERS for Getting Started | 01/04/12 | 30/06/12 | OERs for each topic area developed and shared via website and/or other appropriate |  | All |
| Make resources available internally and externally | 01/07/12 | 31/07/12 | Create a collection of generic OERs to support transition to HE | 4 | All |
| WORKPACKAGE 6: Objective: To evaluate the effectiveness of resources used | 01/08/12 | 30/09/12 |  |  | All |
| Online evaluation of resources | 01/08/12 | 15/09/12 |  |  |  |
| Interviews with staff and students | 15/09/12 | 30/09/12 | Contribute to full evaluation of Getting Started 2012 | 5 |  |
| WORKPACKAGE 7: Objective: To develop strategy for embedding OER practice in support for transition | 01/09/12 | 31/10/12 |  |  | AH |
|  | 01/09/12 | 31/10/12 | Guide for staff on use of OERS to support transition | 6 | AH |

# Members of Project Team:

| Name | Role |
| --- | --- |
| Andy Hagyard (AH) | Team Leader |
| Oonagh Monaghan (OM) | ASL |
| Marie Nicholson (MN) | ASL |
| Adele Beeken (AB) | ASL |
| Marishona Ortega (MO) | ASL |
| Tracey Newby (TN) | ASL |
| Judith Elkin (JE) | ASL |
| Charlotte ? | Student |
| To be confirmed | Academic Reps |