JISC/HEA WORK PACKAGE

| WORKPACKAGES | Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Establishing the project |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Affordances of repository services for storage |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish what support other teams can expect |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Checklist of motivations for producing OER |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guide to metadata standards |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Acronym list |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Quality Assurance |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: <23/01/12>

Project completion date: <31/10/12>

Duration: <10> months

| Work package and activity | Earliest start date | Latest completion date | Outputs (clearly indicate deliverables & reports in bold | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| WORKPACKAGE1 : Establishing the project | 01/02/12 | 31/03/12 |  |  |  |
| Develop a schedule of team meetings | 01/02/12 | 08/02/12 | Schedule available on Website |  | JB |
| Allocate tasks and responsibilities | 01/02/12 | 15/02/12 | To be decided at first meeting |  |  |
| Establishment of Team Website/blog | 01/02/12 | 31/03/12 | Website available and full of useful info |  | All |
| WORKPACKAGE 2: Affordances of repository services Objective: To provide a guide to the options OER authors have for storing their resources |  |  |  |  |  |
| Conduct a literature search | 24/01/12 | 28/02/12 | Bibliography on OER storage |  | JB, PS |
| Investigate affordances of national/local repositories | 01/03/12 | 31/04/12 | Test materials stored in different repositories and reports on ease of use |  | JW,JM |
| Devise and present a program of workshops | 01/02/12 | 30/09/12 | Programme published on web site, and workshops delivered | Yes | All (JW to lead) |
| 4. Produce a report and guide for users | 01/05/12 | 31/10/12 | Glossy booklet (plus other media) designed for users. | Yes | ALL |
| WORKPACKAGE 3: Establish what support other teams can expect Objective: To provide a realistic guide to what support we can provide |  |  |  |  |  |
| 5.Early meeting to discuss what we can offer | 30/01/12 | 03/02/12 | Meeting (Post initial project meeting) |  | ALL |
| 6.Write this up collaboratively | 06/02/12 | 29/02/12 | Report | Yes | JB |
| 7. Circulate to other teams | 01/03/12 | 01/03/12 |  |  | JB |
| WORKPACKAGE 4: Checklist of motivations for producing OER Objective: To provide a visual and text based walkthrough for staff wishing to create an OER |  |  |  |  |  |
| 8. Literature search on OERs | 01/03/12 | 30/06/12 |  |  | PS, JW, JB |
| 9. Write Literature Review on OERS | 01/07/12 | 31/08/12 | A literature review | Yes | PS, JW, JB |
| 10. Produce walkthrough (In appropriate format) | 01/07/12 | 31/10/12 | An app, or other product (format to be decided) | Yes | JM, JW, |
| WORKPACKAGE 5: Guides to metadata standards, copyright and licensing. Objective: To explain why metadata is essential to staff, and get them in the habit of thinking about these matters |  |  |  |  |  |
| 11. Produce a template for adding metadata to OERS | 01/03/12 | 01/07/12 |  |  | PS, JB |
| 12. Adapt same for different repositories | 01/04/12 | 01/10/12 | Template to be added to an OER | Yes | JW. JM |
| WORKPACKAGE 6: Objective: To provide a list of useful acronyms for authors of OERs |  |  |  |  |  |
| 13. Related to WP1 – identify useful acronyms | 01/03/12 | 30/06/12 | Acronym list | Yes | ALL |
| 14. Add to final booklet | 01/02/12 | 31/10/12 | Appendix to booklet | Yes | JB |
| WORKPACKAGE 7: Objective: Quality assurance & Evaluation |  |  |  |  |  |
| 15. Survey other teams 2 twice during project to assess quality of our support and ensure we’re meeting their needs | 01/04/12 | 01/08/12 | Telephone surveys of other teams, prior to project team meetings |  | JB |
| 16. Decide appropriate actions if any based on results | 08/04/12 | 08/08/12 | Feedback to team meetings |  | JB |
| WORKPACKAGE 8: Sharing and sustainability | 01/02/12 | 31/10/12 |  |  |  |
| 17. Ensure all outputs stored in appropriate repositories with appropriate metadata etc. | 01/02/12 | 31/10/12 | A set of open resources on creating open resources |  | All |
| 18. Produce a report evaluating the process of OER discovery, production and hosting and making recommendations about the advantages of doing this and how Lincoln (and others) can incorporate these into future academic processes. | 01/02/12 | 31/10/12 | Report to Senior Management team/possible publication |  | All |

Members of Project Team:

| Name | Role |
| --- | --- |
| Julian Beckton (JB) | Team Leader |
| Joss Winn (JW) | Developer/researcher |
| Jamie Mahoney (JM) | Developer |
| Paul Stainthorp (PS) | Researcher |