# JISC/HEA WORK PACKAGE

| WORKPACKAGES | Month | 1 Jan | 2 Feb | 3 Mar | 4 Apr | 5 May | 6 Jun | 7 Jul | 8 Aug | 9 Sep | 10 Oct | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objectives: |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Manage project in order to ensure successful outcomes and identify dissemination routes throughout the project time line. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: Investigate the philosophy and practice of open education; digitally-inclusive practice; similar course provision in other HEIs and identify, scope and evaluate relevant OER. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3: Develop the online short course/Part One: Teaching and Learning in the Digital Age: theory and practice re online communication, collaborative working and producing and reusing digitally-inclusive teaching and learning material |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4: Develop the online short course/Part Two: Teaching and Learning in the Digital Age: theory and practice re online assessment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5: Establish the online short course: Teaching and Learning in the Digital Age |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Disseminate project results and outcomes internally and externally. |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: <January 2012>

Project completion date: <October 2012>

Duration: <10> months

| Work package and activity | Earliest start date | Latest completion date | Outputs (clearly indicate deliverables & reports in bold | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| WORKPACKAGE 1: Objective: 1. Manage project in order to ensure successful outcomes |  |  |  |  |  |
| 1. Set up schedule of meetings for project duration | Jan | Feb | Project team has agreed meeting dates | 1 | AM |
| 2. Agree project identity (name/title/logo/online presence etc). | Jan | Feb | Project title, logo and identity in place and promoted on http://oer.blogs.lincoln.ac.uk | 1 | All |
| 3. Maintain overview of project, keeping records of progress and reporting on progress as required | Jan | Oct | Progress reports Project web site | 1 | AM |
| 5. Agree dissemination routes and publicity pathways to run throughout the project | Jan | Oct | Prog Teaching & Learning Com University staff newsletter article Conference presentations/posters (internal and external) publication peer-reviewed journal | 1 | All team |
| 6. Identify and agree project evaluation processes | Sept | Oct | Project evaluation report |  |  |
| 7. Develop sustainability and exit strategy so project work is embedded into departmental practice | Jan | Oct | Project final report | 1 | All Team |
| WORKPACKAGE 2: Objective:Investigate the philosophy and practice of open education; digitally- inclusive practice; similar course provision in other HEIs and identify, scope and evaluate relevant OER. |  |  |  |  |  |
| Research the philosophy and practice of the open education movement, ie, CapeTown declaration, David Wiley, William and Flora Hewlitt and others. | Feb | Apr | Learning materials on OER resource Guide to staff and students Centre | 2 | AM JW (Team Six) SW |
| Develop effective search strategies and identify relevant repositories in relation to HE teaching and learning. | Feb | Apr | Workshop Learning materials on OER resource Centre Guide to staff and students Centre | 2 | AM JW JB (Team Six) AM |
| Identify and obtain information around existing course provision for teaching staff in other HEIs. | Feb | Apr | Brief summary document detailing existing provision |  | AM |
| Research Creative Commons Licences, copyright, fair use and IP with regard to using digital content found online | Feb | Apr | Workshop Learning materials on OER resource Centre Guide to staff and students | 2 | AM JW PS (Team Six) |
| Identify inclusive practice with OER for teaching staff including signposting for further support and guidance, eg, LexDis and TechDis | Feb | Apr | Workshop Learning materials on OER resource Centre Guide to staff and students | 2 | AM |
| WORKPACKAGE 3: Objective: Develop the online short course/Part One: Teaching and Learning in the Digital Age: theory and practice re online communication, collaborative working and producing and reusing digitally-inclusive teaching and learning material |  |  |  |  |  |
| Develop and draft the short course specification around Part 1 | Mar | Apr | Short course specification Part One completed | 3 | AM |
| Evaluation of existing OER | Mar | Apr | Record of group feedback and report on findings | 3 | All Team led by AM and RDB |
| Develop and draft course outline for Part One | May | Jun | Course content licenced as OER | 3 | All Team led by AM and RDB |
| Pilot and revise course specification and outline | May | Jun | Questionnaire results Record of group feedback | 3 | AmE, VC, MS, AM |
| WORKPACKAGE 4: Objective: Develop the online short course/Part Two: Teaching and Learning in the Digital Age: theory and practice re online assessment |  |  |  |  |  |
| Develop and draft the course outline around Part Two | Mar | Apr | Short course specification Part Two completed | 3 | AM |
| Evaluation of existing OER | Mar | Apr | Record of group feedback and report on findings | 3 | All Team led by AM and RDB |
| Develop and draft course outline for Part Two | May | Jun | Course content licenced as OER | 3 | All Team led by AM and RDB |
| Pilot and revise course specification and outline | May | Jun | Questionnaire results Record of group feedback | 3 | AmE, VC, MS, AM |
| WORKPACKAGE 5: Objective:Establish the online short course: Teaching and Learning in the Digital Age |  |  |  |  |  |
| Finalise and produce the application for short course approval, short course specification and Participant Handbook | Feb | Jun | Key documents for short course approval completed |  | AM |
| Seek short course approval through University processes | Feb | Jun | Validated short course (15 M CATS) entered onto University Portfolio and available online for academic and professional support staff |  | AM |
| WORKPACKAGE 6: Objective:Disseminate project results and outcomes internally and externally. |  |  |  | 8 | All Team |
| Produce Project Report | Sept | Oct | Report presented at T&L Committee |  |  |
| Publicise internally to all staff (1) | Oct | Oct | Article in staff magazine |  |  |
| Publicise internally to new staff (2) – following liaison with Staff Learning and Development/HR | Oct | Oct | Inclusion in Academic Staff Handbook |  |  |
| Inclusion of course in Teacher Education Programme Provision | Sept | Onwards | Short course details on CERD website: Teacher Education section |  |  |
| Conference presentation | Sept | onwards | Conference presentation 2012/2013 |  |  |
| Paper for publication | Sept | Onwards | Paper in peer reviewed journal |  |  |

# Members of Project Team:

| Name | Role |
| --- | --- |
| Aileen Morris | Team Leader |
| Roger de Bank | Staff |
| Helen Davies | Staff |
| Crystal Walker | Staff |
| Ian Ulyatt | Staff |
| Zara Healy | Staff |
| Jenny Dagg | Staff |
| Valeria Carroll, | Student |
| Amira Elnokaly | Student |
| Mike Shaw | Student |