JISC/HEA WORK PACKAGE

Before completing this template please note:

- The Project Management Guidelines have detailed instructions for preparing project plans and work packages..

- Please expand tables as appropriate.

- Fill in the information in the document header – project name, document version, and date.

- Text in italics is explanatory and should be deleted in completed documents.

| WORKPACKAGES | Month | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sept | Oct | Beyond Project end |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Project management |  | X | X | X | X | X | X | X | X | X | X |  |
| 2: Staff awareness |  | X | X | X |  |  |  |  |  |  |  |  |
| 3: Student awareness |  |  | X | X | X |  |  |  |  |  |  |  |
| 4: Literature review scope |  |  | X | X | X | X | X | X | X |  |  |  |
| 5: Contribution to OER |  |  |  | X | X | X | X | X | X | X | X | X |
| 6: Student Contribution |  | X | X | X | X | X | X | X | X | X | X | X |
| 7: Dissemination |  |  |  |  |  | X | X | X | X | X | X | X |
| 8: Sustainability |  |  |  |  |  |  |  | X | X | X | X | X |

Project start date: January 2012

Project completion date: Oct 2012

Duration: 10 months

| Work package and activity | Earliest start date | Latest completion date | Outputs (clearly indicate deliverables & reports in bold | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| WORKPACKAGE 1: Objective:Organise and manage project | Jan | Oct |  |  |  |
| Finalise team members and agree project ethos and title | Jan | Jan | First draft of project |  | Team leader |
| Prepare work package and agree with team and overall project leader | Jan | End Jan | Project work package to SW |  | Staff team |
| Put in place project management structures and set up meeting schedule. | Jan | Beginning Feb | Create schedule and disseminate to team members |  | Team Leader |
| Make links with other teams in the wider project | Jan | Mar | Discussions with other team leaders |  | Staff team |
| Maintain overview of project and manage events and dissemination | Jan | Oct | Progress reports, records of progress, notes from meetings. |  | Staff team |
| Ensure that project outcomes and processes are disseminated and available | Jan | Oct | School meetings, school colloquia, conference presentations, possible paper in peer reviewed journal |  | Staff team |
| Ensure all aspects of the project are fully evaluated and fed back to overall project management, project participants and other interested parties | Jan | Oct and beyond | Progress reports, team meetings, records of work and discussions with ‘stakeholders’. |  | Staff team |
| Ensure suitable exit strategy so that work of project is embedded into practice and sustained into the future | Jan | Oct and beyond | Project final report |  | Staff team |
| WORKPACKAGE 2: Objective: Researching levels of staff awareness |  |  |  |  |  |
| To ascertain staff awareness of the existence of OER’s on the subject of employability through an email survey. | Jan | Mar | Design and distribution of the staff questionnaires. |  | Staff team |
| Evaluation of staff survey data. | Feb | Mar | Write up of data evaluation and working towards a shared definition of OER’s and where to search for them. |  | Staff team |
| Create list of criteria for selecting OER’s - for students – and define concept of employability for this project | Jan | Mar | Production of workable list and definition of ‘employability’. |  | Staff team |
| Evaluate evidence of the pros and cons of using OER’s in order to be able to discuss any concerns and criticisms in an informed and valid manner. | Jan | Mar | Collation of short ‘literature’ review about OER’s. |  | Staff team |
| WORKPACKAGE 3 : Objective: Researching levels of student awareness |  |  |  |  |  |
| To ascertain student awareness of the existence of OER’s on the subject of employability through a focus group with students. | Feb | Mar | Arrange a focus group. Evaluate language data. |  | Staff team and students |
| Evaluation of student focus group data | Feb | Apr | Write up of data evaluation |  | Staff team and students |
| WORKPACKAGE 4: Objective: Lit review/scope |  |  |  |  |  |
| Defining an appropriate evaluation process to assess the availability and utility of current OER’s on ‘employability’ | Feb | Mar | Creation of working definitions and statement of process. |  | Staff team and students |
| To explore the availability and accessibility of OERs on the subject of ‘employability’ using the evaluation process defined in 7. | Feb | Apr | Scope current OER content on the subject of employability. Collate findings creating an accessible source list. |  | Staff team and students. |
| To explore the utility of OER’s on ‘employability’ using the evaluation process defined in 7. | Feb | Apr | As above. |  | Staff team and students |
| To investigate how OER’s may be effectively linked to current teaching and learning relating to a specific employability module in the undergraduate criminology curriculum entitled Criminology in the Professions. | Feb | May | Compile a suitable list of OER resources related specifically to the Criminology in the Professions module (CIP). |  | Staff team and students. |
| To investigate how such materials could be used more broadly to enhance other social science programmes within the university. | Feb | May | Compile a suitable list of OER resources related more broadly to other social science programmes and beyond. |  | Staff team |
| Explore ways of disseminating such materials for use by the wider academic community. | Feb | May | Choose and set up a suitable open source environment or utilise one that is currently available to upload such materials. |  | Staff team |
| Look into developing appropriate commentaries to facilitate use of appropriate available OER’s on ‘employability’. | Feb | May | Link commentaries to suitable sources. |  | Staff team and students. |
| Identifying any gaps in the available OER’s on ‘employability’ and considering whether materials currently used in learning and teaching at UoL could use used to enhance existing OER’s or produce new packages under OER licence. | Feb | June | Collate potential sources |  | Staff team |
| WORKPACKAGE 5: Objective: To contribute to current OER content on ‘employability’. |  |  |  |  |  |
| Assess current teaching and learning materials on the module Criminology in the Professions and assess whether these would contribute to the existing OER’s | Mar | Aug (but on going) | Collate potential sources |  | Staff team |
| Assess and operationalize any changes and developments required to existing materials to make these relevant in the context of the OER ethos. | Mar | Aug (but on going) | Make suitable sources ‘OER ready’ |  | Staff team and students. |
| WORKPACKAGE 6: Objective: Student contribution to OERs |  |  |  |  |  |
| Facilitate student input into resource production in the context of ‘student as producer’. | Jan | Jul (but on going) | Collate student contributions. |  | Staff team and students. |
| Work with the students in the research team to investigate how both students and staff access, use and apply OER’s and identify whether there are differences between staff and student experiences. | Jan | Jul (but on going) | Production of written overview and reflection. |  | Staff team and students. |
| WORKPACKAGE 7: Objective: Dissemination |  |  |  |  |  |
| Arrange an event with staff and students from the School of Social Sciences to discuss the findings from the project. | May | July | Event takes place. |  | Staff team and students |
| Submit an abstract to produce a paper for the SRHE conference on the project (June 2012 for Dec Conference). | June | Dec conference | Successful acceptance of paper. |  | Staff team |
| Production of Journal article | June | On going | Successful acceptance of article |  | Staff team |
| WORKPACKAGE 8: Objective: Exit strategy ensuring sustainability |  |  |  |  |  |
| Identification and application of relevant practice from all projects that can be applied to Criminology in the Professions module | Jul | On going | Integration of appropriate practice into CIP module |  | Staff on CIP module |
| Identification and application of relevant practice from all projects that can be applied to other modules across the School of Social Sciences | Jul | On going | Integration of appropriate practice across School of Social Sciences |  | Staff Team |
| Identification and application of relevant practice from all projects that can be applied in UoL careers. | Jul | On going | Integration of appropriate practice in UoL Careers |  | Mandy Jones |

Members of Project Team:

| Name | Role |
| --- | --- |
| Jill Jameson Team Leader | SL in Criminology; Co-ordinator Criminology in the Professions. |
| Kate Strudwick | SL in Criminology: Staff on Criminology in the Professions. |
| Sue Bond-Taylor | SL in Criminology: Staff on Criminology in the Professions. |
| Jan Gordon | SL in Criminology: Co-ordinator Criminological Project and other criminology modules |
| Claire Randerson | SL in International Relations: Course Leader for International Relations |
| Mandy Jones | Senior Careers Officer at UoL |
| Student representative | Level 2 student studying Criminology in the Professions |
| Student representative | Level 2 student studying Criminology in the Professions |