# JISC/HEA WORK PACKAGE

| WORKPACKAGES | Month | 1 Jan | 2 Feb | 3 Mar | 4 Apr | 5 May | 6 Jun | 7 Jul | 8 Aug | 9 Sep | 10 Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Project management Organise the project activities among the team members to ensure the quality of the process and achievement of the targets Management of the project activities to among the team members to ensure the quality of the process and achievement of the targets |  |  |  |  |  |  |  |  |  |  |  |
| 2: Definitions Defining OER for the team (including where to find OER repositories and how to search them) Defining criteria for Reflection, reflective thinking, writing etc Defining rationale for focus on reflection in Semester A Year One |  |  |  |  |  |  |  |  |  |  |  |
| 3: Review Review the available materials to support and develop reflective writing during the first year of study (searching through repositories what OER is out there) Merge this task with the one below |  |  |  |  |  |  |  |  |  |  |  |
| 4: Making the decision regarding the existing OER and adapting or creating a new one – this is about evaluating OER so will need a criteria to evaluate against |  |  |  |  |  |  |  |  |  |  |  |
| 5: Redesigning and development of the new OER materials to support reflective writing – something here about identification of an effective learning experience (which includes inclusion e.g. learning preferences, accessibility etc) |  |  |  |  |  |  |  |  |  |  |  |
| 6: Evaluation of the experience of embedding OER practice for Department/School/College and HEA/JISC |  |  |  |  |  |  |  |  |  |  |  |
| 7: Dissemination of the results at the end of the project and sharing our best practice and embedding it in the curriculum |  |  |  |  |  |  |  |  |  |  |  |

Project start date: 9th January 2012

Project completion date: 31st October 2012

Duration: <9> months

| Work package and activity | Earliest start date | Latest completion date | Outputs (clearly indicate deliverables & reports in bold | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| WORKPACKAGE 1: Objective: Organise and manage project activities |  |  |  |  |  |
| 1. Identify the staff team members and allocation of roles | 09th January 2012 | 27th January 2012 | A list of team members who are committed to the project (circulate contact details) | 1 | Julie Burton |
| Identify students willing to take part in project | 09th January 2012 | 3rd February 2012 | Names of two students identified and added to the team members list (circulate contact details) | 1 | Valeria Carroll |
| 3. Complete the necessary documentation supporting the project (e.g. work package document) | 09th January 2012 | 31st October 2012 | Completed documentation to be submitted to Sue Watling for signing off | 1 | Julie Burton and Valeria Carroll |
| 4. Organisation of the project procedures (e.g. arranging team meeting schedule; meetings with critical friends, meetings with the project Co-ordinator, meetings with other teams) | 09th January 2012 | 28th February 2012 | Proposed schedules of meetings on various levels. | 1 | Julie Burton and team |
| 5. Create projects identity (title, logo, online representation) | 09th January 2012 | 13th February 2012 | Clear title, logo, online presence available to view by others | 1 | Team members |
| 6. Keeping the record of the project progress (starting, process and progress, review, evaluation, dissemination, collaboration with others) | 09th January 2012 | 31st October 2012 | Progress reports and team meeting minutes | 1 | Julie Burton and Valeria Carroll |
| 7. Maintain focus on dissemination of the project outcomes (e.g. via school meetings, etc.) | 09th January 2012 | 31st October 2012 | School meeting, various faculty committees, annual appraisal, internal communications, staff magazine and external sources, e.g. conferences and possible publication in peer review journal | 1 | Team members |
| 8. Create opportunities for the outcomes of the project are embedded in current practice | 09th January 2012 | 31st October 2012 | Amending and reviewing curricula in various programmes to incorporate the outcomes of the project as an example of best practice of using OER for early reflective writing | 1 | Team members |
| WORKPACKAGE 2: Objective: Defining OER for the team (where to find OER repositories and how to look for them) | January 2012 | 13th February 2012 | A short set of guidance notes to support staff around understanding of OER and how to look for them | 2 | Jason Tsai |
| Define OER for Health & Social Care | January 2012 | 13th February 2012 | Clear definition conveyed via team meeting | 2 | Julie Burton |
| Identify repositories for OER | January 2012 | 13th February 2012 | Disseminate list of identified existing repositories at team meeting | 2 | Jason Tsai |
| Development of searching skills for OER | January 2012 | 13th February 2012 | Appraise team of best practice regarding OER searching | 2 | Valeria Carroll |
| WORKPACKAGE 3: Objective: Review the available materials to support and develop reflective writing during the first year of study (searching through repositories if there |  |  |  |  |  |
| Identifying the criteria for reflective writing in semester A year one | January 2012 | March 2012 | Produce document for team as a working document for the project | 3 | Julie Burton |
| Mapping potential OER materials to the criteria | January 2012 | March 2012 | Produce document for team which maps potential OER | 3 | Jason Tsai |
| Involve students to evaluate existing OER | January 2012 | March | Students to produce short evaluation document of relevant existing OER | 3 | Jayne Kelly |
| WORKPACKAGE 4: Objective: Making the decision regarding using the existing OER and/or adapting or creating a new ones |  |  |  |  |  |
| Evaluation of the existing OER materials and identification which ones can be repurposed | March 2012 | April 2012 | Produce a pull of OER to be repurposed for specific criteria for reflective writing | 4 | Julie Burton |
| Identification of the gap areas in OER materials | March 2012 | April 2012 | Produce a list of the gap areas which need to be covered using OER | 4 | Valeria Carroll |
| Consider digital divides in accessing OER materials | March 2012 | April 2012 | Produce a set of guidelines how we attempt to overcome divisiveness | 4 | Jason Tsai |
| WORKPACKAGE 5: Objective: If required redesigning and development of the new OER materials to support reflective writing |  |  |  |  |  |
| Select appropriate areas to be covered and the appropriate media for this purpose | April 2012 | May 2012 | Produce document listing new/updated OER materials | 5 | Jason Tsai |
| Identifying Best Practice with Learning Design | April 2012 | May 2012 | Dissemination to team the best practice examples – produce a set a guidelines | 5 | Valeria Carroll |
| 3. Create at least one OER material to be put in the repository | March 2012 | September 2012 | OER document produced and added to repository | 5 | Jayne Kelly |
| WORKPACKAGE6: Objective: Evaluation of the OER |  |  |  |  |  |
| Evaluation of the OER with staff |  | June-July | Evaluation questionnaire report where the results of the evaluation of OER by staff are discussed | 6 | Julie Burton |
| Evaluation of the OER with students |  | September - October | Evaluation questionnaire report where the results of the evaluation of OER by students are discussed | 6 | Julie Burton |
| WORKPACKAGE 7: Objective: Dissemination of the results and sharing our best practice and embedding it in the curriculum |  |  |  |  |  |
| Looking for the best ways to disseminate results in the faculty | March | September 2012 | Faculty symposium date booked | 7 | Valeria Carroll |
| Use ‘Getting Started’ to introduce potential students to reflection and OER | January 2012 | July 2012 | Produce OER for ‘Getting Started’ programme | 7 | Julie Burton |
| Looking for potential dissemination of the results across the University via Teaching Committees, internal staff communications and additional publicity | September 2012 | December 2012 | University OER seminar date booked and added to Daily Alerts | 7 | Julie Burton |
| Implementation of the OER materials in the teaching of the modules where learning outcomes are devoted to reflective writing | Jan 2012 | April 2012 | Revised indicative reading and inclusion of OER session in lecture schedule | 7 | Jason Tsai |
| Further implementation of the OER for the modules that require minor modification to incorporate reflective writing | Jan 2012 | April 2012 | Apply for minor modifications to Core Skills module to include LO on reflection | 7 | Julie Burton |

# Members of Project Team:

| Name | Role |
| --- | --- |
| Julie Burton | Team Leader |
| Dr Valeria Carroll | Team member |
| Jayne Kelly | Team member |
| Jason Tsai | Team member |
| Adrian Croft | Team Member |
| Charlotte Payne | Team member (student) |
| Bryre Clark | Team member (student) |